## Project Plan
ID # | Task Name | Description ¦ Action | Assigned | Status | Notes
1 | GitHub |  | Gus |  | https://github.com/trigus00/Higher_Learning/invitations
|  | Establish project 2 GitHub | Gus | Completed | https://github.com/trigus00/Higher_Learning/invitations
2 | Data
| Identify Data Sets |  | team
| Data Set 1 | Kaggle: Crime and Incarceration in the United States: 21st century state crime and prison custody statistics | Richard | Completed | https://www.kaggle.com/christophercorrea/prisoners-and-crime-in-united-states
| Data Set 2 | The Annie E. Casey Foundation: Kids Count Data Center: Fourth grade reading achievement levels in the United States | Richard | Completed | https://datacenter.kidscount.org/data/tables/5116-fourth-grade-reading-achievement-levels?loc=1&loct=2#detailed/2/2-52/false/871,573,36,867,38,18,16,14,13/1185,1186,1187,1188/11560
| Data Set 3 | American Fact Finder from Census Gov: Annual Survey of School System Finances: Per Pupil Amounts for Current Spending of Public Elementary-Secondary School Systems by State | Richard | Completed | https://factfinder.census.gov/faces/tableservices/jsf/pages/productview.xhtml?src=bkmk
| Data Set 4 | Urban Institute: State and Local Finance Data Query System | Richard ¦ Gus | Completed | https://www.urban.org/policy-centers/cross-center-initiatives/state-and-local-finance-initiative/interactive-data-tools
| Research | Follow up with Vera Data: Correctional Spending | Richard |  | Vera only had 2010 and 2015 data
| Research | Follow up with NASBO Data: Correctional Spending | DJ |  | Have not heard back from NASBO account sign up
| Download Data | Kaggle: Crime and Incarceration in the United States: 21st century state crime and prison custody statistics | DJ | Completed
| Download Data | The Annie E. Casey Foundation: Kids Count Data Center: Fourth grade reading achievement levels in the United States | DJ | Completed
| Download Data | American Fact Finder from Census Gov: Annual Survey of School System Finances: Per Pupil Amounts for Current Spending of Public Elementary-Secondary School Systems by State | Richard | Completed
| Download Data | Urban Institute: State and Local Finance Data Query System | Richard | Completed
3 | Identify visualizations
1. Map
2. Similar to D3
3. Plotly
4 | determine processing of data
5 | determine data/process flow
6 | HTML template
|  | Review/Select HTML/Webpage template | Team | Completed
|  | Adapt HTML and files for Heroku ready | DJ
7 | create ¦ code
|  | HTML set up | DJ
index.html
python flask app
javascript
css
database
|  | GeoMapping/Leaflet - testing out coding | Gus
8 | Deploy to Heroku
|  | test push | DJ
Push project
User Acceptance Testing
9 | Rehearse presentaiton
10 | Readme

## Notes
20191007 Project Notes |  |  |  | Rough Draft |  | spurious correlation
|  |  | 1 | identify data sets | team name
node is local version of JavaScript |  |  | 2 | identify visualizations | set up github
|  |  | 3 | determine processing of data
|  |  | 4 | determine data/process flow
We're running JavaScript from |  |  | 5 | Select HTML template | https://colorlib.com/preview/#waterboat |  | download; push to Heroku
|  |  | 6 | create ¦ code
github
index.html
don't use with npm install this library |  |  |  | python flask app
javascript
css
3 visualizations |  |  |  | database
|  |  | 7 | deploy to Heroku
|  |  | 8 | Create presentation
1. Map |  |  | 9 | Rehearse presentaiton
2. Similar to D3
3. Plotly
leaflet choropleth |  | << map of literarcy rates
https://www.kaggle.com/christophercorrea/prisoners-and-crime-in-united-states
https://datacenter.kidscount.org/data/tables/5116-fourth-grade-reading-achievement-levels?loc=1&loct=2#detailed/2/2-52/false/871,573,36,867,38,18,16,14,13/1185,1186,1187,1188/11560
10/9/2019: from now till Saturday
Richard: | Follow up with Vera Data: Correctional Spending
Daniel: | Follow up with NASBO Data: Correctional Spending
Work on HTML/Webpage template, and push to Heroku
Gus: GeoMapping/Leaflet - testing out coding
Daniel Jones 8:07 PM
Project 2: Higher Learning (Richard Harris, Gustavo Mendoza, Daniel Jones): Education¦Literacy Rates and Incarceration Rates:
Data Sources:
(1) https://www.kaggle.com/christophercorrea/prisoners-and-crime-in-united-states;
(2) https://datacenter.kidscount.org/data/tables/5116-fourth-grade-reading-achievement-levels?loc=1&loct=2#detailed/2/2-52/false/871,573,36,867,38,18,16,14,13/1185,1186,1187,1188/11560,
(3) American Fact Finder from Census Gov,
(4) currently looking for correction spending, can use https://www.bjs.gov/index.cfm?ty=pbdetail&iid=4556
Visualizations:
1. Map
2. Similar to D3
3. Plotly
GitHub: https://github.com/trigus00/Higher_Learning/invitations
datacenter.kidscount.org
Fourth grade reading achievement levels ¦ KIDS COUNT Data Center
Table data for Fourth grade reading achievement levels(176 kB)
Project 2 and Project 3
D3 chart creation optional
Project 2 and Project 3
HTML
Bootstrap
Plotly
FLASK
DB (postgres/mongodb)
Herokku