## Project Plan
ID # | Task Name | Description ¦ Action | Assigned | Status | ETA | Notes
1 | GitHub |  | Gus |  |  | https://github.com/trigus00/Higher_Learning/invitations
| Set up Team GitHub | Establish project 2 GitHub | Gus | Completed |  | https://github.com/trigus00/Higher_Learning/invitations
| GitHub Higher_Learning SSH | SSH code/link | n/a | n/a |  | git@github.com:trigus00/Higher_Learning.git
2 | Data
| Identify Data Sets |  | team | Completed
| Data Set 1 | Kaggle: Crime and Incarceration in the United States: 21st century state crime and prison custody statistics | Richard | Completed |  | https://www.kaggle.com/christophercorrea/prisoners-and-crime-in-united-states
| Data Set 2 | The Annie E. Casey Foundation: Kids Count Data Center: Fourth grade reading achievement levels in the United States | Richard | Completed |  | https://datacenter.kidscount.org/data/tables/5116-fourth-grade-reading-achievement-levels?loc=1&loct=2#detailed/2/2-52/false/871,573,36,867,38,18,16,14,13/1185,1186,1187,1188/11560
| Data Set 3 | American Fact Finder from Census Gov: Annual Survey of School System Finances: Per Pupil Amounts for Current Spending of Public Elementary-Secondary School Systems by State | Richard | Completed |  | https://factfinder.census.gov/faces/tableservices/jsf/pages/productview.xhtml?src=bkmk
| Data Set 4 | Urban Institute: State and Local Finance Data Query System: cost per prisoner by state (2006-2016) | Richard ¦ Gus | Completed |  | https://www.urban.org/policy-centers/cross-center-initiatives/state-and-local-finance-initiative/interactive-data-tools
| Data Set 5 | Urban Institute: State and Local Finance Data Query System: state expenditures on students by state (2006-2016) | Richard ¦ Gus | Completed |  | https://www.urban.org/policy-centers/cross-center-initiatives/state-and-local-finance-initiative/interactive-data-tools
| Data Set 6 | National Center for Education Statistics: Digest of Education Statistics | Richard ¦ Gus | Completed |  | https://nces.ed.gov/programs/digest/d13/tables/dt13_203.20.asp
| Data Set 7 | Kaggle: U.S. Education Datasets: Unification Project: K-12 financial, enrollment, and achievement data in one place | Richard ¦ Gus | Completed |  | https://www.kaggle.com/noriuk/us-education-datasets-unification-project#states_all.csv
| Data Set 8 | National Center for Education Statistics: Digest of Education Statistics: Potential for other work: Reading Achievement | Richard ¦ Gus | Completed |  | https://nces.ed.gov/programs/digest/current_tables.asp
| Research | Follow up with Vera Data: Correctional Spending | Richard | Terminated |  | Vera only had 2010 and 2015 data
| Research | Follow up with NASBO Data: Correctional Spending | DJ | Terminated |  | Have not heard back from NASBO account sign up
| Research | Rutgers: Toward Common Frameworks and Methods for Evaluating State School Finance Systems |  |  |  | https://aasa.org/uploadedFiles/AASA_Blog(1)/BBaker.AASA.July_8_2019.pdf: Uses E classifications; defines E027
| Download Data | Kaggle: Crime and Incarceration in the United States: 21st century state crime and prison custody statistics | DJ | Completed |  | Use Prisoner Count
| Download Data | The Annie E. Casey Foundation: Kids Count Data Center: Fourth grade reading achievement levels in the United States | DJ | Completed |  | column F & C
| Download Data | American Fact Finder from Census Gov: Annual Survey of School System Finances: Per Pupil Amounts for Current Spending of Public Elementary-Secondary School Systems by State | Richard | Completed ¦ Pass |  | Will not use for project, but will retain for optional use in the future
| Download Data | Urban Institute: State and Local Finance Data Query System: cost per prisoner by state (2006-2016) | Richard | Completed |  | Column C
| Download Data | Urban Institute: State and Local Finance Data Query System: state expenditures on students by state (2006-2016) | Richard | Completed |  | Backup to Kaggle Education data set; Column E027
| Download Data | National Center for Education Statistics: Digest of Education Statistics | Richard ¦ Gus | Completed ¦ Pass |  | Will not use for project, but will retain for optional use in the future
| Download Data | Kaggle: U.S. Education Datasets: Unification Project: K-12 financial, enrollment, and achievement data in one place | Richard ¦ Gus | Completed |  | Use Enrollment and Total Expenditures
| Time Period | 2006 to 2016 | Team | Completed
3 | Identify visualizations
| 1. Heat Map | Education and Incarceration | Gus |  | 10/14/2019 6:30pm
| 2. Similar to D3 | Transition | DJ |  | 10/14/2019 6:30pm
| 3. Plotly | Bar Chart | Richard |  | 10/14/2019 6:30pm
4 | determine processing of data
5 | determine data/process flow
6 | HTML template
|  | Review/Select HTML/Webpage template | Team | Completed
|  | Adapt HTML and files for Heroku ready | DJ
7 | create ¦ code
| HTML set up |  | DJ
| PostgreSQL | Set up tables | DJ
|  | Kaggle: Crime and Incarceration in the United States: 21st century state crime and prison custody statistics |  |  |  | Use Prisoner Count
|  | The Annie E. Casey Foundation: Kids Count Data Center: Fourth grade reading achievement levels in the United States |  |  |  | column F & C
|  | Urban Institute: State and Local Finance Data Query System: cost per prisoner by state (2006-2016) |  |  |  | Column C
|  | Kaggle: U.S. Education Datasets: Unification Project: K-12 financial, enrollment, and achievement data in one place |  |  |  | Use Enrollment and Total Expenditures
| PostgreSQL | Import data | DJ
index.html
python flask app
javascript
css
database
| GeoMapping/Leaflet - testing out coding |  | Gus
8 | Deploy to Heroku
| test push |  | DJ
Push project
User Acceptance Testing
9 | Rehearse presentaiton
10 | Readme

## Notes
20191007 Project Notes |  |  |  | Rough Draft |  | spurious correlation
|  |  | 1 | identify data sets | team name
node is local version of JavaScript |  |  | 2 | identify visualizations | set up github
|  |  | 3 | determine processing of data
|  |  | 4 | determine data/process flow
We're running JavaScript from |  |  | 5 | Select HTML template | https://colorlib.com/preview/#waterboat |  | download; push to Heroku
|  |  | 6 | create ¦ code
github
index.html
don't use with npm install this library |  |  |  | python flask app
javascript
css
3 visualizations |  |  |  | database
|  |  | 7 | deploy to Heroku
|  |  | 8 | Create presentation
1. Map |  |  | 9 | Rehearse presentaiton
2. Similar to D3
3. Plotly
leaflet choropleth |  | << map of literarcy rates
https://www.kaggle.com/christophercorrea/prisoners-and-crime-in-united-states
https://datacenter.kidscount.org/data/tables/5116-fourth-grade-reading-achievement-levels?loc=1&loct=2#detailed/2/2-52/false/871,573,36,867,38,18,16,14,13/1185,1186,1187,1188/11560
10/9/2019: from now till Saturday
Richard: | Follow up with Vera Data: Correctional Spending
Daniel: | Follow up with NASBO Data: Correctional Spending
Work on HTML/Webpage template, and push to Heroku
Gus: GeoMapping/Leaflet - testing out coding
Daniel Jones 8:07 PM
Project 2: Higher Learning (Richard Harris, Gustavo Mendoza, Daniel Jones): Education¦Literacy Rates and Incarceration Rates:
Data Sources:
(1) https://www.kaggle.com/christophercorrea/prisoners-and-crime-in-united-states;
(2) https://datacenter.kidscount.org/data/tables/5116-fourth-grade-reading-achievement-levels?loc=1&loct=2#detailed/2/2-52/false/871,573,36,867,38,18,16,14,13/1185,1186,1187,1188/11560,
(3) American Fact Finder from Census Gov,
(4) currently looking for correction spending, can use https://www.bjs.gov/index.cfm?ty=pbdetail&iid=4556
Visualizations:
1. Map
2. Similar to D3
3. Plotly
GitHub: https://github.com/trigus00/Higher_Learning/invitations
datacenter.kidscount.org
Fourth grade reading achievement levels ¦ KIDS COUNT Data Center
Table data for Fourth grade reading achievement levels(176 kB)
Project 2 and Project 3
D3 chart creation optional
Project 2 and Project 3
HTML
Bootstrap
Plotly
FLASK
DB (postgres/mongodb)
Herokku